## All projects
SNo | Projects on consideration | Status | Actuals /Expected cost | Amount Paid | Outstanding | Start Month | Completion month | Vendors | Remarks | Type of project | Accounts
1 | Lift Upgrades(Major electronic,PCB/relays) | Completed | 390000 | 390000 | 0 | 2018-11-01 | 2018-12-01 | Otis | Amount paid to OTIS by cheque, completed on 30th Sep,2018 | Manitenanace /Upgrades | Maitenanace (ICICI-99)
2 | Completion Certificates | Hold | 567000 | 331000 | 236000 | 2018-12-01 | 2019-04-01 | Design & Design | Architect Garg has been contracted to provide the completion certificates, initiatlly expected by 31st dec. 4 laks total + 18% GST=472000 + 95000(DDA),clreance from Fire departmen still awaited. | Project | Projects( DSCB-51)
3 | Fire Upgrades | Completed | 1263820 | 1263820 | 0 | 2018-12-01 | 2020-08-01 | Fire Axe Engineers | All payments inclduing additional made inclduing the retention of 130403 | Projects | Projects( DSCB-51)
4 | Solar Power Installation | Completed | 1595993 | 1446143 | 149850 | 2019-11-01 | 2021-01-01 | Uneecops Pvt Ltd. | retained the outstanding amount | Project | Development (DSCB-58) & Maintenance (367745)
5 | Terrace Water Proofing(A Block) | Completed | 306000 | 282452 | 23548 | 2019-02-01 | 2020-06-01 | Rahul & Arun | Vendor never turned up for outstanding amount of 23548, thisamount is forefeited | Manitenanace | Projects( DSCB-51)
6 | Terrace Water Proofing(B Block) | Completed | 196070 | 196070 | 0 | 2017-12-01 | 2018-05-01 | Bhagwan Swain | Completed by two vendors (11000+86070) | Manitenanace | Projects( DSCB-51)
| ***Terrace Water Proofing(C Block) | Approved-Deferred | 571000 | [5 empty] | Vendor shortlisted | Maintenance
7 | CCTV camera instalattion(32 cameras) | Completed | 321060 | 331060 | -10000 | 2017-03-01 | 2017-04-01 | Radient Infotech | society area exculding basement & terrace | Projects | Development (DSCB-58)
8 | Additional camera instalation(17 cameras) | Completed | 140000 | 130000 | 10000 | 2019-12-01 | 2020-01-01 | Radient Infotech | Basement and terrace cameras inclduing online and C block community hall | Projects | Development (DSCB-58)
9 | ***Surronding Pathways repair | Approved-Deferred | 1000000 | [5 empty] | Sub committee needs to be formed | Manitenanace Projects(Upgrades)
10 | ***Whitewashing and painting of entire societies | Approved | 650000 | [5 empty] | Sub committee formed | Manitenanace Projects(Upgrades)
11 | Changing electric Panel and intercom panel board & electrcial trench in entrance of each block | Completed | 218368 | 218368 | 0 | 2019-04-01 | 2020-01-01 | Radient Infotech | In front of the entrace of the each wing,the electric and telephone wires are dangeraously dangling out without cover, security hazards in rainy season due to electric short circuit Rs.42000 for intercom boxex & Rs.40000 fo making trench in entrance of each block Rs.136368 for electrical panel | Manitenanace/Upgrades | Maitenanace (ICICI-99) (71K) & Projects(DSCB-51)
12 | Trafic Signages | Completed | 20245 | 20245 | 0 | 2018-05-01 | 2019-12-05 | Mahir Signages | Done in two phases of aprox 10K each | Projects | Projects( DSCB-51)
13 | Earthing under Ground | Completed | 180000 | 180000 | 0 | 2017-03-01 | 2017-04-01 | ARS solution | ARS solution | Manitenanace (Periodic) | Projects( DSCB-51)
14 | Earthing terrace | Completed | 207717 | 207717 | 0 | 2017-02-01 | 2017-06-01 | Radient Infotech |  | Manitenanace (Periodic) | Projects( DSCB-51)
15 | F15 car parking and Koodadan renovation | Completed | 139388 | 139388 | 0 | 2018-05-01 | 2018-06-01 | Daily workers | this work done by daily workers. | Projects | Projects( DSCB-51)
16 | Major repairs of Electrical system | Completed | 394645 | 394645 | 0 | 2017-04-01 | 2017-06-01 | Radient Infotech | Cable testing,changing of MCCB,Fuses, fuse bases, transformer service, & others electrcal works. | Manitenanace (Periodic) | Projects( DSCB-51)
17 | Whitewash Office Lounge | Completed | 39828 | 39828 | 0 | 2018-11-01 | 2018-12-01 | Munna Painter | Electrical 11802, labor 11000,materail 17026 | Manitenanace(Periodic) | Development (DSCB-58)
18 | Whitewash Guradroom | Completed | 23877 | 23877 | 0 | 2019-01-01 | 2019-02-01 | Munna Painter | Labor 7000,matarial 7676,electrical 9201 | Manitenanace (Periodic) | Development (DSCB-58)
19 | DG set repair | Completed | 70000 | 70000 | 0 | 2017-11-01 | 2017-12-01 | Radient Infotech | Includes Body repairs | Manitenanace (Periodic) | Projects( DSCB-51)
20 | Whitewash office room | Completed | 14365 | 14365 | 0 | 2019-02-01 | 2019-03-01 | Munna Painter | Material 6365,labor 8000 | Manitenanace (Periodic) | Development (DSCB-58)
22 | *** Lift complete modernization with ARD | Approved-Deferred | 3000000 | 0 |  |  |  | Otis | This is complete modernozation involves Drive,ARD,Door sensors,Chequered plate floorings. Can go big bang or phasewise depending on cash flow | Manitenanace Projects(Upgrades)
23 | Purchasing projector | Completed | 52000 | 52000 | 0 | 2019-08-19 | 2019-08-19 | EPSON | Shorliested EPSON | Projects | Development (DSCB-58)
24 | Shaft area Repair /renovation in front of all 6 lifts | Completed | 110000 | 104530 | 5470 | 2019-10-20 | 2020-10-20 | Ram Raj | Full paid,TDS adjusted from remaining | Manitenanace (Periodic) | Projects( DSCB-51)
25 | Shed for Covering Shafts (Terrace for all 6 wings) | Completed | 51978 | 51978 | 0 | 2019-10-01 | 2020-10-20 | Atma Sah | Including paint | Manitenanace (Periodic) | Maintetance (ICICI -99)
26 | HT & LT Major Repair and periodic services of Transformer | Completed | 182134 | 182134 | 0 | 2020-03-03 | 2020-09-20 | Mr. Chopra & S.S. Electricals | Service of transfomer room, dehydration, Change MCCB, Oiling changing copler, relay & Hooter etc. SS Electriacsl(Sarderjee) did the remainingb work | Manitenanace (Periodic) | Maintenance (ICICI -99)
27 | Community Hall (Concrete Slab Between C101&C102) | Completed | 128000 | 128000 | 0 | 2020-12-20 | 2020-12-20 | Ram Raj | Sub committee submitted the quotaions of 3 vendors. This is Quoataion of L1 | Development | Development (DSCB-58)
28 | Community Hall (Laying Kota Stone) | Completed | 236900 | 236900 | 0 | 2021-01-01 | 2021-02-02 | Ram Raj | Sub committee submitted the quotaions of 3 vendors. This is Quoataion of L1 | Development | Development (DSCB-58)
29 | ***Community Hall (Covering with half Walls and Glass Windows ) | New | 0 | [5 empty] | Sub committee needs to be formed | Development
30 | ***Community Hall (Interiors including laying elctical and sewage line) | New | 0 | [5 empty] | Sub committee needs to be formed | Development
31 | ***Community Hall (Interiors Kitchen and Bathroom) | New | 0 | [5 empty] | Sub committee needs to be formed | Development
32 | ***Community Hall (Installing AC ,lightings other amenities) | New | 0 | [5 empty] | Sub committee needs to be formed | Development
33 | *** Strictural Refreseth including basement Roof repair | Approved | 1500000 |  |  |  |  | Arun | Sub committee submitted the quotaions of 3 vendors (55 rs per sq ft). This is for B3 only. Reconsidering to be taken care of along with Strcutural audit outcome | Development
34 | Covering Electric Junctions in all floors outside(earlier exposed) | Completed | 95000 | 95000 | 0 | 2021-01-01 | 2021-01-01 | Ajeet Jha | Ajeet Jha offered | Manitenanace (Periodic) | Maintenance (ICICI -99)
35 | Structural Audit | Completed | 290000 | 249000 | 41000 | 2021-03-01 | 2021-06-06 | Sanrachna | As per quotations | Infrastrcure | Infrasturcture fund
36 | *** Major retrofit work after Recommendation of Structural Audit | New | 0
37 | *** Automatic Boom Barrier with RFID | New
38 | *** Public addressing systems (mike in each block) | New
39 | Lifts floor renovations (Chequired plate) | Completed | 127440 | 127440 | 0 | 2021-08-01 | 2021-08-01 | Otis | Negotiated by Mr Vinod Bhandari | Manitenanace /Upgrades | Maintenance (ICICI -99)
40 | ***Solar Plant installation in B and C block | Approved-Deferred | 3300000 | [5 empty] | As per Pradip Sarma's proposal | Development
41 | *** Conversion of Genset from Diesel to CNG | New
42 | *** Grit wash repairs | Approved | 150000 | [5 empty] | Amounts quoted lumsum | Maintenance
43 | *** Replacing existing water pieplines | New | [6 empty] | Amounts quoted lumsum | Maintenance
44 | Repair of C block Terrace parapet wall | Completed | 86262 | 81949 | 4313 | 2021-03-01 | 2021-04-01 | Arun | retains 4313 | Maintenance | Maintenance (ICICI -99)
45 | Replacing broken glasses and Fixing all other with putty infrony of all stairs | Completed | 63780 | 63780 | 0 | 2020-08-01 | 2020-09-01 | Seetram |  | Manitenanace (Periodic) | Maintenance (ICICI -99)
46 | Repainting Car Parking Slot | Completed | 162390 | 162390 | 0 | 2020-12-20 | 2020-12-20 | Manamkrishna | Sub committee (Mr Dhyan Singh,Mr Prateek Barua) proposed quotation of one vendor | Maintenanace(periodic) | Projects( DSCB-51)
47 | ***Fixing water seepage A block 7th floors | Approved | 150000
48
49
50 | Additional One camera and replacement of gate camera | Completed | 14700 | 14700 | 0 | 2021-03-21 | 2021-03-21 | Radient Infotech |  | Development | Development
51 | Wireless Mike for sound system |  | 7837 |  |  |  |  | Amazon(Karansher pvt ltd) | Rs.5880 for purchasing wireless mike & Rs.1957 for mike covers & extension wire. | Development | Maintenance (ICICI -99)
| Total |  | 7121960 | 6897779 | 224181
`
*** High level ball park figure.
Status | New
Initial aproval of MC ( also nonimating sub committed to asses the cost and feasibility)
Sub committee formed
WIP (weekly interim status report to be submitted to MC on progess and status (scope and work order,quotaition ,evaluations etc)
Final Recommendations submitted
Final Approvals from MC

## Fund Positions
Fund Postion As On 20th Dec ,2020
S.No | Accounts Head | A/C No. | Bank Name | Balance in Savings | Fixed Deposit
1 | Ground Rent/Maintanace(DCSB) | A/C-17 | DSCB | 88805 | 3696558
2 | Extension Project | A/C-51 | DSCB | 12078 | 0
3 | Devleopment Fund(DSCB) | A/C-58 | DSCB | 161123 | 660578
4 | Maintanance(ICICI) | A/C-99 | ICICI | 616901 | 1200000
5 | Garden Fund(ICICI) | A/C-38 | ICICI | 6400 | 0
6 | Infrastruture Fund(ICICI) | A/C-87 | ICICI | 0 | 0
| Grand Total |  |  | 885307 | 5557136
Fund Position As On 18th Sep ,2021
S.No | Accounts Head | A/C No. | Bank Name | Balance in Saving | Fixed Deposite
1 | Ground Rent(DCSB)(Old Maintanance) | A/C-17 | DSCB | 15085 | 3748395 | 51837
2 | Extension Project (DCSB) | A/C-51 | DSCB | 32629 | 100000 | 100000
3 | Devleopment Fund(DSCB) | A/C-58 | DSCB | 75334 | 844106 | 183528
4 | Maintanance(ICICI) | A/C-99 | ICICI | 315332 | 2028333 | 828333
5 | Garden Fund(ICICI) | A/C-38 | ICICI | 31891 | 0 | 0
6 | Infrastruture Fund(ICICI) | A/C-87 | ICICI | 79536 | 400000 | 400000
| Grand Total |  |  | 549807 | 7120834 | 1563698

## Identified
Projects Identified
***Community Hall (Covering with half Walls and Glass Windows )
***Community Hall (Interiors including laying elctical and sewage line)
***Community Hall (Interiors Kitchen and Bathroom)
***Community Hall (Installing AC ,lightings other amenities)
*** Major retrofit work after Recommendation of Structural Audit
*** Automatic Boom Barrier with RFID
*** Public addressing systems (mike in each block)
*** Conversion of Genset from Diesel to CNG
*** Replacing existing water pieplines

## Completed
SNo | Projects Completed | Status | Actuals Cost | Completion month
1 | Lift Upgrades(Major electronic,PCB/relays) | Completed | 390000 | 2018-12-01
2 | Fire Upgrades | Completed | 1263820 | 2020-08-01
3 | Solar Power Installation | Completed | 1595993 | 2021-01-01
4 | Terrace Water Proofing(A Block) | Completed | 306000 | 2020-06-01
5 | Terrace Water Proofing(B Block) | Completed | 196070 | 2018-05-01
6 | CCTV camera instalattion(32 cameras) | Completed | 321060 | 2017-04-01
7 | Additional camera instalation(17 cameras) | Completed | 140000 | 2020-01-01
8 | Changing electric Panel and intercom panel board & electrcial trench in entrance of each block | Completed | 218368 | 2020-01-01
9 | Trafic Signages | Completed | 20245 | 2019-12-05
10 | Earthing under Ground | Completed | 180000 | 2017-04-01
11 | Earthing terrace | Completed | 207717 | 2017-06-01
12 | F15 car parking and Koodadan renovation | Completed | 139388 | 2018-06-01
13 | Major repairs of Electrical system | Completed | 394645 | 2017-06-01
14 | Whitewash Office Lounge | Completed | 39828 | 2018-12-01
15 | Whitewash Guradroom | Completed | 23877 | 2019-02-01
16 | DG set repair | Completed | 70000 | 2017-12-01
17 | Whitewash office room | Completed | 14365 | 2019-03-01
18 | Purchasing projector | Completed | 52000 | 2019-08-19
19 | Shaft area Repair /renovation in front of all 6 lifts | Completed | 110000 | 2020-10-20
20 | Shed for Covering Shafts (Terrace for all 6 wings) | Completed | 51978 | 2020-10-20
21 | HT & LT Major Repair and periodic services of Transformer | Completed | 182134 | 2020-09-20
22 | Community Hall (Concrete Slab Between C101&C102) | Completed | 128000 | 2020-12-20
23 | Community Hall (Laying Kota Stone) | Completed | 236900 | 2021-02-02
24 | Covering Electric Junctions in all floors outside(earlier exposed) | Completed | 95000 | 2021-01-01
25 | Structural Audit | Completed | 290000 | 2021-06-06
26 | Lifts floor renovations (Chequired plate) | Completed | 127440 | 2021-08-01
27 | Repair of C block Terrace parapet wall | Completed | 86262 | 2021-04-01
28 | Replacing broken glasses and Fixing all other with putty infrony of all stairs | Completed | 63780 | 2020-09-01
29 | Repainting Car Parking Slot | Completed | 162390 | 2020-12-20
30 | Additional One camera and replacement of gate camera | Completed | 14700 | 2021-03-21
7121960

## Completed FY20-21
SNo | Projects Completed | Status | Actuals Cost | Completion month
1 | Lift Upgrades(Major electronic,PCB/relays) | Completed | 390000 | 2018-12-01
1 | Fire Upgrades | Completed | 1263820 | 2020-08-01
2 | Solar Power Installation | Completed | 1595993 | 2021-01-01
3 | Shaft area Repair /renovation in front of all 6 lifts | Completed | 110000 | 2020-10-20
5 | Shed for Covering Shafts (Terrace for all 6 wings) | Completed | 51978 | 2018-05-01
6 | HT & LT Major Repair and periodic services of Transformer | Completed | 182134 | 2017-04-01
7 | Community Hall (Concrete Slab Between C101&C102) | Completed | 128000 | 2020-01-01
8 | Community Hall (Laying Kota Stone) | Completed | 236900 | 2020-01-01
9 | Covering Electric Junctions in all floors outside(earlier exposed) | Completed | 95000 | 2019-12-05
10 | Structural Audit | Completed | 290000 | 2017-04-01
11 | Lifts floor renovations (Chequired plate) | Completed | 127440 | 2017-06-01
12 | Repair of C block Terrace parapet wall | Completed | 86262 | 2018-06-01
13 | Replacing broken glasses and Fixing all other with putty infrony of all stairs | Completed | 63780 | 2017-06-01
14 | Repainting Car Parking Slot | Completed | 162390 | 2018-12-01
15 | Additional One camera and replacement of gate camera | Completed | 14700 | 2019-02-01
16 | DG set repair | Completed | 70000 | 2017-12-01
17 | Whitewash office room | Completed | 14365 | 2019-03-01
18 | Purchasing projector | Completed | 52000 | 2019-08-19
4 | Shed for Covering Shafts (Terrace for all 6 wings) | Completed | 51978 | 2020-10-20
5 | HT & LT Major Repair and periodic services of Transformer | Completed | 182134 | 2020-09-20
6 | Community Hall (Concrete Slab Between C101&C102) | Completed | 128000 | 2020-12-20
7 | Community Hall (Laying Kota Stone) | Completed | 236900 | 2021-02-02
8 | Covering Electric Junctions in all floors outside(earlier exposed) | Completed | 95000 | 2021-01-01
9 | Structural Audit | Completed | 290000 | 2021-06-06
10 | Lifts floor renovations (Chequired plate) | Completed | 127440 | 2021-08-01
11 | Repair of C block Terrace parapet wall | Completed | 86262 | 2021-04-01
12 | Replacing broken glasses and Fixing all other with putty infrony of all stairs | Completed | 63780 | 2020-09-01
13 | Repainting Car Parking Slot | Completed | 162390 | 2020-12-20
14 | Additional One camera and replacement of gate camera | Completed | 14700 | 2021-03-21
4408397

## Approved
SNo | Approved List of Projects | Status | Expected cost
1 | ***Terrace Water Proofing(C Block) | Approved | 571000
2 | Surronding Pathways repair | Under Consideration | 1000000
3 | ***Whitewashing and painting of entire societies | Approved | 650000
4 | Lift complete modernization with ARD | Under Consideration | 5000000
5 | *****Building Structural retrofit (Most essentials -basement Roof repair) | Approved | 2000000
6 | *** Structural Audit | Completed | 350000
7 | Solar Plant installation in B and C block | Under Consideration | 3300000
8 | *** Grit wash repairs (Outer top floors) | Approved | 150000
9 | ***Fixing water seepage A block 7th floors | Approved-Maintenanace | 150000
| Conversion of Genset from Diesel to CNG | Under Consideration | 200000
| Automatic Boom Barrier with RFID | Under Consideration | 150000
| Community Hall at C block | Under Consideration | 700000
***Community Hall (Covering with half Walls and Glass Windows )
***Community Hall (Interiors including laying electical and sewage line)
***Community Hall (Interiors Kitchen and Bathroom)
***Community Hall (Installing AC ,lightings other amenities)
2800000